## Sheet1
Tasks
Start date | End date | Description | Duration in days
2023-10-04 | 2023-10-11 | Phase 1: Identify needs | 7 | 2023-11-03 | 10 | All preperation complete
2023-10-17 | 2023-10-31 | Phase 2: Planning | 14 | 2023-11-03 | 95
2023-11-07 | 2024-01-02 | Phase 3: Execution | 56 | 2024-01-27 | 10 | Project complete
2024-01-10 | 2024-01-24 | Phase 4: Testing | 14 | 2024-01-27 | 95
Phase 1: The initial meeting with the counselor identified customer inputs will include, click a link to get his email or refer a concern for another student, summarize school counseling and counselor resources, a page for articulation agreements for post-secondary education
Phase 2: Create a storyboard for the website and customize how it looks to present to customer for approval.
Phase 3: Writing the HTML code and implementation of CSS. The execution includes usage of hamburger menus, jump links, configuration tabs, active links, defaulted links
Phase 4: The final step will be to make sure that everything on the website is functioning properly and fixing any errors that may exist
Formulas:
End date = [Start date]+[Duration in days]